## 工作表 1 - CSE110M260T6 Schedule
CSE110M260T6 Schedule
| Task | Status
Week4 | Compose user stories from the requirements provided by our clients | Done
| Complete the schedule planning | Done
| Update with client | Done
Week5 | Set up android studios on each member’s computer | Done
| Draw out the UML for class inheritance | Done
| Group division | Done
Update with client
Week6 | Create Main activity (home screen) — Add newAlarm button | Done
| Create Alarm class — basic functionality | Done
| Update with client | Done
Week7 | Create Database — unit tests | In progress
| Create addAlarm activities — bound with database | In progress
| Create turningOff activities | In progress
Update with client
Week8 | Add alarmManager | 0 progress
| Add ringTone — unit tests | 0 progress
| Refine UI — make connections between activities | 0 progress
| Professor meeting — prototype demo | 0 progress
| Update with client — prototype demo | 0 progress